## Diagrama de Gantt
	TIME PLANNING

	AUTHOR	Daniel Benedí García				COURSE					DA150X
	SUPERVISOR	Alexander Kozlov				DATE					25/02/22

						FEBRUARY					MARCH					APRIL					MAY					JUNE
						7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8
ID	TASK	BEGINNING	END	DURATION	PORCENTAJE COMPLETADO	FASE UNO					FASE DOS
						WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12					WEEK 13					WEEK 14					WEEK 15					WEEK 16					WEEK 17
						L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X

1.1	Choose research topic	07/02/22	11/02/22	4	100%
1.2	Write Project Plan	07/02/22	25/02/22	18	100 %					1
1.3	Study previous research	12/02/22	17/02/22	5	100 %	17 March 2021
1.4	Resources Retrieval	22/02/22	14/03/22	22	100 %	18 March 2021
1.5	Environment Setup	10/03/22	16/03/22	6	100 %	19 March 2021
1.6	Implement basic models and test	17/03/22	10/04/22	23	100 %	20 March 2021
1.7	Define properly heuristics to use	08/04/22	17/04/22	9	100 %	21 March 2021
1.8	Extend basic models with heuristics	15/04/22	01/05/22	16	100 %	22 March 2021
1.9	Experiment and acquire metrics	03/04/22	08/05/22	35	100 %	23 March 2021
	Analysis	05/05/22	14/05/22	9
	Report	05/05/22	08/06/22	33					2					3					6
	Peer review	19/05/22	25/05/22	6					4
	Presentation	25/05/22	01/06/22	6					5

						NOTES
						1		Hand-in of project specification
						2		Submission of Public Science Abstract
						3		Hand-in of students' reports for peer review
						4		Hand-in of students' peer reviews
						5		Student conference
						6		Hand-in of students' final reports